## MVP hierarchy
MVP implementation hierarchy
Proposed plan from Weeks 5–6. All items are unstarted. Resolve product/design gates before dependent implementation.
ID | Parent ID | Type | Work item | Completion check | Depends on ID | Status | Gate / constraint | Slice target (min) | Source key | Verification evidence
MVP |  | MVP | Translation review web MVP | One reviewer completes one small Arabic-to-English document, saves and resumes corrections, and indicates completion. |  | Proposed |  |  | W5 §6–8; W6 §17
1 | MVP | Epic | Agree the bounded experiment | Approved scope, UX and measurable acceptance criteria. |  | Proposed | Product choices unresolved |  | W5 §6–8, §12
1.1 | 1 | Story | Resolve product limits | Agreed format, size, completion and failure rules are explicit. |  | Proposed |  |  | W5 §6–8, §12
1.1.1 | 1.1 | Task | List format and document-size options | Record supported inputs, rejection cases and candidate size limits. |  | Proposed |  | 5 | W5 §6–8, §12
1.1.2 | 1.1 | Task | Confirm input boundaries with product owner | Record explicit format and size decisions; leave unresolved choices open. | 1.1.1 | Proposed |  | 5 | W5 §6–8, §12
1.1.3 | 1.1 | Task | Define translation trigger and recovery | Specify explicit or automatic start, failure display, retry and partial-result policy. | 1.1.2 | Proposed |  | 5 | W5 §6–8, §12
1.1.4 | 1.1 | Task | Define completion and draft retention | Resolve paragraph/document completion and minimum original-draft/history behavior. | 1.1.3 | Proposed |  | 5 | W5 §6–8, §12
1.2 | 1 | Story | Define the acceptance experiment | Reviewed PRD and UX describe observable success. | 1.1.4 | Proposed |  |  | W5 §6–8, §12
1.2.1 | 1.2 | Task | Write core workflow acceptance examples | Cover upload, draft, ordered review, correction, save, resume and completion. | 1.1.4 | Proposed |  | 5 | W5 §6–8, §12
1.2.2 | 1.2 | Task | Annotate error and save states in wireframes | Include invalid upload, translation error and unsuccessful save. | 1.2.1 | Proposed |  | 5 | W5 §6–8, §12
1.2.3 | 1.2 | Task | Agree pilot success measures | Record quality/usefulness and timing measures with owner-approved thresholds; examples are not targets. | 1.2.2 | Proposed |  | 5 | W5 §6–8, §12
2 | MVP | Epic | Define architecture and contracts | Reviewed design supports the bounded workflow. | 1 | Proposed | Architecture choices unresolved |  | W6 §4–7, §12–15
2.1 | 2 | Story | Select a minimal implementation design | Stack, storage and release/access assumptions have explicit rationale. | 1 | Proposed |  |  | W6 §4–7, §12–15
2.1.1 | 2.1 | Task | Compare viable stack and database options | Compare workflow fit, durability, consistency, cost and maintainability; distinguish course defaults. | 1 | Proposed |  | 5 | W6 §4–7, §12–15
2.1.2 | 2.1 | Task | Record selected architecture and access boundary | Document selected stack/storage and private-preview access model with alternatives. | 2.1.1 | Proposed |  | 5 | W6 §4–7, §12–15
2.1.3 | 2.1 | Task | Define book and paragraph schema | Specify keys, ownership, source/draft/edited text, explicit position and chosen completion state. | 2.1.2 | Proposed |  | 5 | W6 §4–7, §12–15
2.1.4 | 2.1 | Task | Define API and consistency contracts | Describe create/read/update payloads, errors, book ownership checks and read-after-save behavior. | 2.1.3 | Proposed |  | 5 | W6 §4–7, §12–15
2.2 | 2 | Story | Create a runnable baseline | Setup, checks and initial persistence can run from documented commands. | 2.1.4 | Proposed |  |  | W6 §4–7, §12–15
2.2.1 | 2.2 | Task | Create minimal backend entry point | A smoke check reaches the backend using the selected runtime. | 2.1.4 | Proposed |  | 5 | W6 §4–7, §12–15
2.2.2 | 2.2 | Task | Create minimal web entry point | Frontend starts and calls the backend smoke endpoint. | 2.2.1 | Proposed |  | 5 | W6 §4–7, §12–15
2.2.3 | 2.2 | Task | Add initial schema migration | Apply selected schema to an empty test store and verify constraints. | 2.2.2 | Proposed |  | 5 | W6 §4–7, §12–15
2.2.4 | 2.2 | Task | Document local run and test commands | A clean-environment walkthrough identifies configuration and secret inputs. | 2.2.3 | Proposed |  | 5 | W6 §4–7, §12–15
3 | MVP | Epic | Upload and organize source | Valid bounded input becomes durably ordered paragraphs. | 2 | Proposed | Depends on approved upstream contracts |  | W5 §7; W6 §5, §7, §12
3.1 | 3 | Story | Validate and create the document | Accepted input creates a book; invalid input is rejected. | 2 | Proposed |  |  | W5 §7; W6 §5, §7, §12
3.1.1 | 3.1 | Task | Implement agreed input validation predicate | Boundary tests cover empty, unsupported and oversized inputs. | 2 | Proposed |  | 5 | W5 §7; W6 §5, §7, §12
3.1.2 | 3.1 | Task | Implement document creation API | Valid fixture returns a stable book ID; invalid fixture creates no usable book. | 3.1.1 | Proposed |  | 5 | W5 §7; W6 §5, §7, §12
3.1.3 | 3.1 | Task | Wire upload form to API | Show accepted result and meaningful validation/server errors. | 3.1.2 | Proposed |  | 5 | W5 §7; W6 §5, §7, §12
3.2 | 3 | Story | Persist paragraph identity and order | Source passages retain stable identity and intended sequence. | 3.1.3 | Proposed |  |  | W5 §7; W6 §5, §7, §12
3.2.1 | 3.2 | Task | Implement agreed paragraph segmentation | Representative Arabic fixture preserves source text and agreed paragraph boundaries. | 3.1.3 | Proposed |  | 5 | W5 §7; W6 §5, §7, §12
3.2.2 | 3.2 | Task | Persist source paragraphs and positions | Saved fixture has stable book/paragraph IDs and explicit unique positions. | 3.2.1 | Proposed |  | 5 | W5 §7; W6 §5, §7, §12
3.2.3 | 3.2 | Task | Return paragraphs in explicit order | Read test returns reading order independently of generated IDs. | 3.2.2 | Proposed |  | 5 | W5 §7; W6 §5, §7, §12
4 | MVP | Epic | Generate a machine draft | External translation produces preserved aligned draft text. | 3 | Proposed | Depends on approved upstream contracts |  | W5 §7; W6 §7, §13
4.1 | 4 | Story | Connect translation provider | A configured external provider maps output to the correct source passage. | 3 | Proposed |  |  | W5 §7; W6 §7, §13
4.1.1 | 4.1 | Task | Define provider adapter and deterministic fake | Success, timeout and malformed-response fixtures exercise one adapter contract. | 3 | Proposed |  | 5 | W5 §7; W6 §7, §13
4.1.2 | 4.1 | Task | Implement external provider request | A bounded permitted sample returns target text; credentials remain server-side. | 4.1.1 | Proposed |  | 5 | W5 §7; W6 §7, §13
4.1.3 | 4.1 | Task | Validate and persist draft alignment | Reject missing/mismatched results and persist successful draft against stable paragraph IDs. | 4.1.2 | Proposed |  | 5 | W5 §7; W6 §7, §13
4.2 | 4 | Story | Handle translation failure safely | Reviewer sees progress/failure and can recover without losing work. | 4.1.3 | Proposed |  |  | W5 §7; W6 §7, §13
4.2.1 | 4.2 | Task | Expose translation state in API | Agreed pending/success/failure states are distinguishable and readable. | 4.1.3 | Proposed |  | 5 | W5 §7; W6 §7, §13
4.2.2 | 4.2 | Task | Display translation state and recovery action | UI exposes the agreed start/retry interaction and useful failure message. | 4.2.1 | Proposed |  | 5 | W5 §7; W6 §7, §13
4.2.3 | 4.2 | Task | Implement safe repeat-request rule | A repeated request follows agreed policy without overwriting reviewer edits. | 4.2.2 | Proposed |  | 5 | W5 §7; W6 §7, §13
4.2.4 | 4.2 | Task | Verify provider failures and partial results | Timeout and partial-failure fixtures preserve existing successful drafts/corrections. | 4.2.3 | Proposed |  | 5 | W5 §7; W6 §7, §13
5 | MVP | Epic | Review aligned paragraphs | Reviewer can compare and edit passages in reading order. | 4 | Proposed | Depends on approved upstream contracts |  | W5 §3, §7; W6 §2, §12
5.1 | 5 | Story | Read source beside target | Arabic source and English target remain correctly paired. | 4 | Proposed |  |  | W5 §3, §7; W6 §2, §12
5.1.1 | 5.1 | Task | Render one aligned paragraph pair | Check Arabic RTL and English LTR text with mixed punctuation and numbers. | 4 | Proposed |  | 5 | W5 §3, §7; W6 §2, §12
5.1.2 | 5.1 | Task | Add ordered paragraph navigation | First/last and previous/next behavior stays paired with the correct source. | 5.1.1 | Proposed |  | 5 | W5 §3, §7; W6 §2, §12
5.1.3 | 5.1 | Task | Handle unavailable draft state | Missing or failed translation cannot appear as a completed translation. | 5.1.2 | Proposed |  | 5 | W5 §3, §7; W6 §2, §12
5.2 | 5 | Story | Correct target text in place | Editing changes the reviewed target while preserving agreed draft behavior. | 5.1.3 | Proposed |  |  | W5 §3, §7; W6 §2, §12
5.2.1 | 5.2 | Task | Bind editable target to paragraph identity | Typing and navigation do not apply edits to a different paragraph. | 5.1.3 | Proposed |  | 5 | W5 §3, §7; W6 §2, §12
5.2.2 | 5.2 | Task | Preserve original draft per agreed contract | Correction updates reviewed text; original output follows the approved retention rule. | 5.2.1 | Proposed |  | 5 | W5 §3, §7; W6 §2, §12
5.2.3 | 5.2 | Task | Test Unicode editing and navigation | Arabic/English symbols, line breaks and paragraph switching preserve intended text. | 5.2.2 | Proposed |  | 5 | W5 §3, §7; W6 §2, §12
6 | MVP | Epic | Save, resume and complete review | Reviewer can stop, return to durable corrections and indicate completion. | 5 | Proposed | Depends on approved upstream contracts |  | W5 §7; W6 §6–7, §13
6.1 | 6 | Story | Save durable corrections | Successful save is visible and latest saved content is readable. | 5 | Proposed |  |  | W5 §7; W6 §6–7, §13
6.1.1 | 6.1 | Task | Implement paragraph update persistence | A saved edit survives a fresh storage connection and subsequent read. | 5 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.1.2 | 6.1 | Task | Enforce operation and book access | Unauthorized operation and wrong-book requests are rejected; permitted reviewer can save. | 6.1.1 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.1.3 | 6.1 | Task | Wire save interaction and dirty state | UI distinguishes unsaved, saving, saved and failed without claiming premature success. | 6.1.2 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.1.4 | 6.1 | Task | Test unsuccessful save recovery | Failed/interrupted save preserves visible edit and supports agreed retry behavior. | 6.1.3 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.2 | 6 | Story | Resume and indicate completion | Reload restores work and completion follows the agreed rule. | 6.1.4 | Proposed |  |  | W5 §7; W6 §6–7, §13
6.2.1 | 6.2 | Task | Load saved document and review position | Reopen restores latest saved content and agreed resume location/behavior. | 6.1.4 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.2.2 | 6.2 | Task | Implement agreed completion state | Persist chosen granularity and transition rules, including edits after completion. | 6.2.1 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.2.3 | 6.2 | Task | Expose completion control and feedback | UI accurately reflects persisted state without adding unapproved export gating. | 6.2.2 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
6.2.4 | 6.2 | Task | Test reload and completion boundaries | Reload, incomplete material and post-completion edits follow the approved acceptance examples. | 6.2.3 | Proposed |  | 5 | W5 §7; W6 §6–7, §13
7 | MVP | Epic | Validate the MVP experiment | Evidence demonstrates workflow and informs the next iteration. | 6 | Proposed | Depends on approved upstream contracts |  | W5 §8; W6 §3, §17; proposed implementation verification
7.1 | 7 | Story | Demonstrate the integrated workflow | End-to-end and recovery evidence is recorded. | 6 | Proposed |  |  | W5 §8; W6 §3, §17; proposed implementation verification
7.1.1 | 7.1 | Task | Run bounded workflow smoke scenario | Upload approved fixture, translate, correct, save, reload and complete with recorded results. | 6 | Proposed |  | 5 | W5 §8; W6 §3, §17; proposed implementation verification
7.1.2 | 7.1 | Task | Run integrated failure scenarios | Record invalid input, provider failure, failed save, wrong-book access and alignment checks. | 7.1.1 | Proposed |  | 5 | W5 §8; W6 §3, §17; proposed implementation verification
7.1.3 | 7.1 | Task | Verify restart durability | Restart replaceable application process; saved source, draft and corrections remain accessible. | 7.1.2 | Proposed |  | 5 | W5 §8; W6 §3, §17; proposed implementation verification
7.2 | 7 | Story | Collect reviewer feedback and hand off | Pilot findings are compared with agreed success measures. | 7.1.3 | Proposed |  |  | W5 §8; W6 §3, §17; proposed implementation verification
7.2.1 | 7.2 | Task | Prepare bounded pilot checklist | Record approved fixture, participant, measures and known limitations. | 7.1.3 | Proposed |  | 5 | W5 §8; W6 §3, §17; proposed implementation verification
7.2.2 | 7.2 | Task | Capture one pilot observation segment | Record observed friction and outcomes; repeat bounded segments as needed for the agreed document. | 7.2.1 | Proposed |  | 5 | W5 §8; W6 §3, §17; proposed implementation verification
7.2.3 | 7.2 | Task | Summarize evidence and next actions | Compare actual pilot measures to agreed criteria; distinguish defects from later enhancements. | 7.2.2 | Proposed |  | 5 | W5 §8; W6 §3, §17; proposed implementation verification

## Scope and use
Scope and use
Topic | Plan guidance | Source / reference
Purpose | Proposed implementation plan for the translation-review case study, not a claim that Week 6 adopted an execution backlog. | W6 §15, §17
Hierarchy | MVP > Epic > Story > Task. IDs and Parent ID retain hierarchy when filtered. Dependencies reference completion of the identified item. | DEC-031
Execution | Tasks are provisional 5-minute implementation/check slices. Split further when a selected stack exposes more work. Parent items are not 5-minute tasks. No project duration is estimated. | Repository AGENTS.md; DEC-031
Tracking | Status and Verification evidence are editable. Proposed means unstarted; record actual evidence before marking complete. No dates or owners are assumed. | DEC-031
Scope | One reviewer, one small Arabic-to-English book/article, web delivery, paragraph-based review. | W5 §6–7
Product gate | Decide input format and size, translation trigger/retry, completion granularity, minimum draft/history behavior and measurable success criteria. | W5 §7–8, §12
Architecture gate | Choose and defend stack/storage, schema, routes, consistency and access model. Course overview describes a production learning path; Weeks 5–6 do not establish a selected case-study stack. | W5 §9; W6 §4–7, §12–15; course overview
Release boundary | Determine private-preview access before implementation. Verify backend operation and book-level access before exposing the application. Deployment is not performed by this plan. | W6 §3, §6
Later scope | Multiple reviewers/roles, adjudication, many-book management, publishing, fine-tuning corpus, offline synchronization and custom distributed scaling. | W5 §2, §4, §6; W6 §8–11, §16
Not automatically required | PDF/OCR, export/download gating, scripture lookup, terminology assistance, TTS and rich diff/history remain unapproved additions. Reassess after the core pilot. | W5 §3, §7; W6 §2
Success | Agree pilot measures before coding. The 30-page/30-minute example and reported throughput are not adopted targets or measured MVP results. | W5 §3, §8
Decision record | DEC-031 remains Pending user review. This workbook proposes sequencing and decomposition without selecting unresolved product or technology choices. | ../../DECISIONS.md#dec-031-mvp-work-item-hierarchy
W5 | Organized Week 5 source: product, workflow, exclusions and open questions. | ../../curriculum/weeks/05/session-notes.md
W6 | Organized Week 6 source: architecture, contracts, storage, consistency and unresolved choices. | ../../curriculum/weeks/06/session-notes.md
Week 5 assignment | PRD and UX deliverables provide design inputs, not completed implementation. | ../../curriculum/weeks/05/homework.md
Week 6 assignment | Database comparison/choice, schema and API contracts precede service internals. | ../../curriculum/weeks/06/homework.md
Course overview | Program-level requirements; reconcile with case-study choices at architecture gate. | ../../CAP 2.0 AI-Native.md
Delivery plan | Runnable baseline and access checks precede later deployment work. | ../../conductor/plan.md